## product backlog
product backlog id | priority | user story id | user story | Assigned to | risk | status | remarks
1 | High Risk | Ecommerce_Login | Login | Santosh | Low Risk | Complete | Done in Sprint 1
2 | High Risk | Ecommerce_product | Search Products | Vijay | High Risk |  | Done in Sprint 2
3 | Medium Risk | Ecommerce_cart | Add to Cart | Charith | Low Risk |  | Done in Sprint 3
4 | Low Risk | Ecommerce_checkout | Checkout | Satya | Low Risk |  | Done in Sprint 4
5 | Medium Risk | Ecommerce_checkout | Order Tracking | Mounika | Medium Risk |  | Done in Sprint 5

## sprint backlog 1
Product Backlog ID | User Story ID | User Story | Task Description | Assigned To | Estimated Time | Actual Time | Status
1 | Ecommerce_Login | As a user, I want to log in with valid credentials to access my account. | 1. Enter valid username and password to log in successfully. | Santosh | 6hrs | 4hrs | Done
|  |  | 2. Display an error message for invalid credentials. | Santosh | 6hrs | 3hrs | Done
|  |  | 3. Remember the user session for future logins. | Santosh | 6hrs | 2hrs | Done
2 | Ecommerce_product | As a user, I want to browse products by categories. | 1. Fetch and display products based on selected categories. | Vijay | 7hrs | ….............. | WIP
|  |  | 2. Implement a search bar for finding specific products. | Vijay | 3hrs | 2hrs | Done
|  |  | 3. Add filters for price, brand, and ratings. | Vijay | 7hrs | 5hrs | Done
3 | Ecommerce_cart | As a user, I want to add/remove items in my shopping cart | 1. Enable adding items to the shopping cart. | Charith | 4hrs | ….............. | WIP
|  |  | 2. Implement "Remove from Cart" functionality. | Charith | 5hrs | ….............. | WIP
|  |  | 3. Update cart quantities dynamically. | Charith | 5hrs | 5hrs | Done
4 | Ecommerce_checkout | As a user, I want to complete the purchase securely through a checkout process. | 1. Collect shipping and payment details. | Satya | 4hrs | 5hrs | WIP
|  |  | 2. Integrate with payment gateways (e.g., PayPal, Stripe) | Satya | 4hrs | 4hrs | Done
|  |  | 3. Send order confirmation email to the user. | Satya | 3.5hrs | 4hrs | Done
5 | Ecommerce_checkout | As a user, I want to track my order after placing it. | 1. Display order status (Processing, Shipped, Delivered). | Mounika | 4hrs | 3hr | WIP
|  |  | 2. Integrate shipment tracking with courier services | Mounika | 5hr | 3hr | Done