## product backlog
product backlog id | priority | user story id | user story | Assigned to | complexity | risk | status | remarks
1 | high | train_booking_01 | login | rajesh |  | low |  | it is done in 1st spirnt
2 | high | train_booking_02 | booking ticket | rakesh |  | high |  | done in 2nd spirnt
3 | high | train_booking_03 | cancel ticket |  |  | low |  | done in 3rd spirnt
4 | low | train_booking_04 | rechedule |  |  | high
5 | low | train_booking_05 | register |  |  | low
payment
insurance
seats availability
tracking
food order

## sprint 1
ProductBacklog id | UserStoryID | User Story Step number | Task Description | Assigned To | Estimate time | Actual Time | Status
1 | tain_booking_01 | 1 | Enter username/emailid and password for login to the portal | rajesh | 5hr | 2hr | completed
|  | 2 | On entering wrong password, it should display invalid credentials | rajesh | 10hr | 3hr | completed
|  | 3 | assign forget password options, an otp will send to email and mobile | rajesh | 5hr | 2hr | completed
2 | train_booking_02 | 1 | enter the valid source and destination ,to get the details details | rakesh | 5hr | 3hr | completed
|  | 2 | filter the train based on timing, price,seats availiblity,… | rakesh | 5hr | 3hr | completed
|  | 3 | select the seat, user can able to add meal (optional) | rakesh | 5hr | 3hr | completed
|  | 4 | add insurance, and user see the preview | rakesh | 10hr | 6hr | completed
|  | 5 | add passenger and it show visibale in the preview page | rakesh | 10hr | 6hr | completed
|  | 6 | As a login user, I can able to add the passenger details , so that I will add the passenger for booking, | rakesh | 10hr | 6hr | completed
3 | train_booking_02 | 1 | add tracking for user to check , in which location he is there , and expected time to reach destination | rajesh | 10hr | 7hr | completed
|  | 2 | add food section to user to order and deliverd to the station | rajesh | 10hr | 7hr | completed